## Master CIP
Project ID | Project Name | Description | Estimated Cost Per Fiscal Year | [5 empty] | Estimated Total Project Cost FY25-30 | Funding Source | Project Location
|  |  | FY25 | FY26 | FY27 | FY28 | FY29 | FY30
EQUIPMENT
E4-66 | GMC Buildings/Grounds | GMC 4-door diesel w. utility bed - needs to pull weight - to replace (#112) | Estimated Cost Per Fiscal Year FY25: 80000 | 80000 | Equip Acqu | PW
E5-60 | Road Sweeper | Street Sweeper Truck | Estimated Cost Per Fiscal Year FY26: 350000 | 350000 | Equip Acqu | PW
E5-61 | Short-Frame Plow | Heavy plow/sander to replace International (#121) | Estimated Cost Per Fiscal Year FY25: 350000 | 350000 | Equip Acqu | PW
E5-62 | Peterbuilt Dump Truck/Plow/Sander | For TRI | Estimated Cost Per Fiscal Year FY27: 475000 | 475000 | Equip Acqu | PW
E5-63 | Skippy Tractor | John Deere Skippy loader box grader tractor - for drainage work & snow/ice removal | Estimated Cost Per Fiscal Year FY25: 150000 | 150000 | Equip Acqu | PW
E5-64 | Light Plant w. Solar | Portable light plant w. solar array | Estimated Cost Per Fiscal Year FY28: 20000 | 20000 | Equip Acqu | PW
E5-65 | GMC Water/Sewer | GMC 3/4 ton long-bed gas pickup with shell - to replace current water truck (#103) | Estimated Cost Per Fiscal Year FY25: 70000 | 70000 | Equip Acqu | PW
E5-69 | Compactors | Bomag BT-35 walk-behind soils compactors (2) | Estimated Cost Per Fiscal Year FY27: 10000 | 10000 | Equip Acqu | PW
E5-70 | Patrol Vehicle Rotation | Per 3-year rotation. | Estimated Cost Per Fiscal Year FY25: 80000 | 80000 | Equip Acqu | SO
E5-71 | Patrol Vehicle Rotation | Per 3-year rotation. | Estimated Cost Per Fiscal Year FY25: 80000 | 80000 | Equip Acqu | SO
E5-72 | Patrol Vehicle Rotation | Per 3-year rotation. | Estimated Cost Per Fiscal Year FY25: 80000 | 80000 | Equip Acqu | SO
E5-73 | Patrol Vehicle Rotation | Per 3-year rotation. | Estimated Cost Per Fiscal Year FY25: 80000 | 80000 | Equip Acqu | SO
E5-74 | Tesla | Part of GSA with Tesla (Tesla is paying for this.) | Estimated Cost Per Fiscal Year FY25: 88000 | 88000 | Equip Acqu | SO
E5-75 | RAM 5500 crew-cab utility | To replace current truck (#130) | Estimated Cost Per Fiscal Year FY25: 125000 | 125000 | Equip Acqu | PW
E5-76 | RAM 5500 crew-cab utility | To replace current truck (#126) | Estimated Cost Per Fiscal Year FY25: 125000 | 125000 | Equip Acqu | PW
E5-79 | Skid Steer Snowblower | Attach to Skid Steer - for tight corners and hard to maneuver areas | Estimated Cost Per Fiscal Year FY25: 9000 | 9000 | Equip Acqu | PW
E5-80 | 125' Boom Lift | For IT & PW - to replace current lift | Estimated Cost Per Fiscal Year FY25: 100000 | 100000 | Equip Acqu | IT/PW
E5-81 | Pickup | Com Dev Code Enforcer Vehicle | Estimated Cost Per Fiscal Year FY25: 50000 | 50000 | Equip Acqu | ComDev
E5-82 | Pickup | IT 1500 | Estimated Cost Per Fiscal Year FY25: 55000 | 55000 | Equip Acqu | IT
E5-83 | Electronic Reader Board | Portable for PW | Estimated Cost Per Fiscal Year FY25: 25000 | 25000 | Equip Acqu | PW
E6-60 | PW Peterbuilt Dump Truck |  | Estimated Cost Per Fiscal Year FY26: 300000 | 300000 | Equip Acqu | PW
E6-61 | PW Service Truck | F550/5500 chassis with service body | Estimated Cost Per Fiscal Year FY26: 150000 | 150000 | Equip Acqu | PW
E6-62 | PW John Deere Loader | To replace TRI loader | Estimated Cost Per Fiscal Year FY26: 230000 | 230000 | Equip Acqu | PW
E6-63 | PW Dump Truck | To replace Ford L9000 with new 10-wheel | Estimated Cost Per Fiscal Year FY26: 425000 | 425000 | Equip Acqu | PW
E6-64 | PW Motor Grader | Road Construction | Estimated Cost Per Fiscal Year FY26: 450000 | 450000 | Equip Acqu | PW
E6-65 | PW Screened Grizzly | Road Construction, rock screeening | Estimated Cost Per Fiscal Year FY26: 40000 | 40000 | Equip Acqu | PW
E6-66 | Patrol Vehicle Rotation | Per 3-year rotation. Some funds recovered auctioning our replaced vehicle. | Estimated Cost Per Fiscal Year FY26: 80000 | 80000 | Equip Acqu | SO
E6-67 | Patrol Vehicle Rotation | Per 3-year rotation. Some funds recovered auctioning our replaced vehicle. | Estimated Cost Per Fiscal Year FY26: 80000 | 80000 | Equip Acqu | SO
E6-68 | Patrol Vehicle Rotation | Per 3-year rotation. Some funds recovered auctioning our replaced vehicle. | Estimated Cost Per Fiscal Year FY26: 80000 | 80000 | Equip Acqu | SO
E6-69 | Com. Dev. Pick-up | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY26: 60000 | 60000 | Equip Acqu | CD
E6-70 | EM UTV | Emergency Management UTV | Estimated Cost Per Fiscal Year FY26: 45000 | 45000 | Equip Acqu | EM
E6-71 | Electronic Reader Board | Portable for PW | Estimated Cost Per Fiscal Year FY26: 25000 | 25000 | Equip Acqu | PW
E7-60 | Service Truck | F550/5500 chassis with service body | Estimated Cost Per Fiscal Year FY27: 130000 | 130000 | Equip Acqu | PW
E7-61 | Water Truck | Currently must switch out water tank with plow hardware each season | Estimated Cost Per Fiscal Year FY27: 300000 | 300000 | Equip Acqu | PW
E7-62 | Motor Grader | John Deere | Estimated Cost Per Fiscal Year FY27: 350000 | 350000 | Equip Acqu | PW
E7-63 | Ditch Compactor | Remote control trench compactor, trench safety | Estimated Cost Per Fiscal Year FY27: 50000 | 50000 | Equip Acqu | PW
E7-64 | Small Backhoe/loader | Small front loader tractor with backhoe for parks' work | Estimated Cost Per Fiscal Year FY27: 60000 | 60000 | Equip Acqu | PW
E7-65 | Road Manager Truck | 3500 HD crew-cab, utility body diesel | Estimated Cost Per Fiscal Year FY27: 125000 | 125000 | Equip Acqu | PW
E7-66 | 5-Yard AWD Dump Truck | With plow prep | Estimated Cost Per Fiscal Year FY27: 250000 | 250000 | Equip Acqu | PW
E7-67 | Tractor Trailer | Peterbuilt Truck and RGN Transport Trailer | Estimated Cost Per Fiscal Year FY27: 300000 | 300000 | Equip Acqu | PW
E7-68 | Vactor Truck | New Vactor Truck to serve north end of county (TRI, LW, PR) | Estimated Cost Per Fiscal Year FY27: 650000 | 650000 | Equip Acqu | PW
E7-69 | Patrol Vehicle Rotation | Per 3-year rotation. Some funds recovered auctioning our replaced vehicle. | Estimated Cost Per Fiscal Year FY27: 80000 | 80000 | Equip Acqu | SO
E7-70 | Patrol Vehicle Rotation | Per 3-year rotation. Some funds recovered auctioning our replaced vehicle. | Estimated Cost Per Fiscal Year FY27: 80000 | 80000 | Equip Acqu | SO
E7-71 | Patrol Vehicle Rotation | Per 3-year rotation. Some funds recovered auctioning our replaced vehicle. | Estimated Cost Per Fiscal Year FY27: 80000 | 80000 | Equip Acqu | SO
E7-72 | Service Equipment | Heavy vehicle lifts for shop | Estimated Cost Per Fiscal Year FY27: 150000 | 150000 | Equip Acqu | PW
E7-73 | Backhoe | John Deere 410 to replace existing unit | Estimated Cost Per Fiscal Year FY27: 250000 | 250000 | Equip Acqu | PW
E7-74 | Loader | John Deere 624 Loader | Estimated Cost Per Fiscal Year FY27: 350000 | 350000 | Equip Acqu | PW
E8-60 | GMC 3500 Truck | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 80000 | 80000 | Equip Acqu | PW
E8-61 | Pickup | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 75000 | 75000 | Equip Acqu | CD
E8-62 | Pickup | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 75000 | 75000 | Equip Acqu | CD
E8-63 | Service Truck | RAM 5500HD/550 crew-cab, crane, service body | Estimated Cost Per Fiscal Year FY28: 225000 | 225000 | Equip Acqu | PW
E8-64 | Staff Vehicle | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 50000 | 50000 | Equip Acqu | CM
E8-65 | Staff Vehicle | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 50000 | 50000 | Equip Acqu | Dispatch
E8-66 | Staff Vehicle | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 50000 | 50000 | Equip Acqu | IT
E8-67 | Staff Vehicle | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 50000 | 50000 | Equip Acqu | PW
E8-68 | Staff Vehicle | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 50000 | 50000 | Equip Acqu | SC
E8-69 | Staff Vehicle | Replace current vehicle per rotation schedule | Estimated Cost Per Fiscal Year FY28: 75000 | 75000 | Equip Acqu | VCTC
E8-70 | Patrol Vehicle | Replace per 3-year rotation. Some funds recovered auctioning replaced vehicle. | Estimated Cost Per Fiscal Year FY28: 80000 | 80000 | Equip Acqu | SO
E8-71 | Patrol Vehicle | Replace per 3-year rotation. Some funds recovered auctioning replaced vehicle. | Estimated Cost Per Fiscal Year FY28: 80000 | 80000 | Equip Acqu | SO
E8-72 | Patrol Vehicle | Replace per 3-year rotation. Some funds recovered auctioning replaced vehicle. | Estimated Cost Per Fiscal Year FY28: 80000 | 80000 | Equip Acqu | SO
E9-60 | Multi-Use Truck | RAM 5500HD plow/dump/sander/crew cab | Estimated Cost Per Fiscal Year FY29: 250000 | 250000 | Equip Acqu | PW
E9-61 | Excavator | 16k lbs | Estimated Cost Per Fiscal Year FY29: 175000 | 175000 | Equip Acqu | PW
E9-62 | Street Sweeper |  | Estimated Cost Per Fiscal Year FY29: 350000 | 350000 | Equip Acqu | PW
E9-63 | Forklift | For TRI | Estimated Cost Per Fiscal Year FY29: 50000 | 50000 | Equip Acqu | PW
E9-64 | Snow Cat | EM/SO/FD/PW back country access, snow rescue, citizen snow resources | Estimated Cost Per Fiscal Year FY29: 60000 | 60000 | Equip Acqu | PW
Equipment Totals Per FY |  |  | 1547000 | 2315000 | 3690000 | 1040000 | 885000 | 0 | 9477000
PROJECTS
P3-01 | Courthouse Fence Repair | Mold and foundry | Estimated Cost Per Fiscal Year FY25: 50000 | 50000 | Capital (R) | VC
P4-07 | Fairgrounds Upgrade | Water/electric installation - Began FY24 | Estimated Cost Per Fiscal Year FY25: 820000 | 820000 | 25/75 Capital/ Grant * | VC
Construction
P4-08 | LW Fiber | Tower/Microwave link - contingent up LW Sr. Center completion | Estimated Cost Per Fiscal Year FY26: 78000 | 78000 | Capital/IT | LW
P4-11 | Lockwood Sr. Center | Demo old/build new facility - Began FY24 | Estimated Cost Per Fiscal Year FY25: 5550000; Estimated Cost Per Fiscal Year FY26: 1000000 | 6550000 | 25/75 Capital/ Grant * | LW
|  |  | Construction | Construction
P4-12 | Fire Station 71 | Construct new - Began FY24 | Estimated Cost Per Fiscal Year FY25: 3000000; Estimated Cost Per Fiscal Year FY26: 2690000 | 5690000 | 25/75 Capital/ Grant * | VC
|  |  | Design/ Construction | Construction
P4-13 | Fuel Tanks | Construction - Replace double-lined fuel tanks at TRI & VC - $315k per site | Estimated Cost Per Fiscal Year FY25: 630000 | 630000 | 75/25 Capital/Fire (R) * | TRI/VC
P4-15 | MTCC Outdoor Reader Board | Replace message board with freestanding electronic reader board | Estimated Cost Per Fiscal Year FY25: 50000 | 50000 | Capital | MT
P4-16 | VCTC Center | Pocket park deck at Black & Howell | Estimated Cost Per Fiscal Year FY25: 130000; Estimated Cost Per Fiscal Year FY26: 1500000 | 1630000 | VCTC * | VC
|  |  | Design | Construction
P4-18 | Com. Dev. Generator | Purchase/Install | Estimated Cost Per Fiscal Year FY25: 100000 | 100000 | Capital (R) | VC
P4-19 | Waste Water Tower Fencing |  | Estimated Cost Per Fiscal Year FY25: 25000 | 25000 | Capital (R) | VC
P4-20 | TRI Monument Signs |  | Estimated Cost Per Fiscal Year FY25: 25000 | 25000 | Capital (R) | TRI
P5-01 | Justice Ct/IT Generator | Purchase/Install - Began FY24 | Estimated Cost Per Fiscal Year FY25: 38500 | 38500 | Capital (R) | VC
P5-02 | Gold Hill Sewer Generator | Purchase/Install - Began FY24 | Estimated Cost Per Fiscal Year FY25: 22000 | 22000 | Capital (R) | GH
P5-03 | VC Parcourse | Installation of exercise course - Miner's Park or new location? Resident request | Estimated Cost Per Fiscal Year FY25: 10000; Estimated Cost Per Fiscal Year FY26: 100000; Estimated Cost Per Fiscal Year FY27: 75000 | 185000 | Capital | VC
|  |  | Planning | Design/Permit | Equipment Purchase
P5-04 | LAN | Network devices, LANs, storage, communications | Estimated Cost Per Fiscal Year FY25: 120000 | 120000 | Capital | Countywide
P5-06 | PW Portable Fencing | Portable fencing and trailer for countywide use | Estimated Cost Per Fiscal Year FY25: 50000 | 50000 | Capital (R) | Countywide
P5-07 | MT Community Center | Construct new metal building to move fire apparatus into. Retrofit current building to community center | Estimated Cost Per Fiscal Year FY25: 246500; Estimated Cost Per Fiscal Year FY26: 3500000; Estimated Cost Per Fiscal Year FY27: 450000 | 4271500 | Capital (R) * | MT
|  |  | Design/Metal building | Construct/ Metal building | Construct current building retrofit
75000
Design/ Current building retrofit
P5-08 | Com. Dev. Parking | Add bollards, bumpers to Com Dev parking | Estimated Cost Per Fiscal Year FY25: 50000 | 50000 | Capital (R) | VC
P5-09 | Com. Dev. Mudroom | ADA/Breezeway to Com Dev main entrance | Estimated Cost Per Fiscal Year FY25: 100000 | 100000 | Capital (R) | VC
P5-11 | VCH Swing Set | Install - resident request | Estimated Cost Per Fiscal Year FY25: 12000 | 12000 | VCH Park Fund 190 (R) | VCH
P5-12 | VCH Community Center | Retrofit current Fire Station 72 bays to Community Center. Add warming kitchen, restrooms, breezeway. | Estimated Cost Per Fiscal Year FY25: 45000; Estimated Cost Per Fiscal Year FY26: 400000 | 445000 | Capital (R) * | VCH
|  |  | Design | Construction
P5-13R | SC Gov. Complex Sign | Change back-side lettering to "Storey County Complex" | Estimated Cost Per Fiscal Year FY25: 5000 | 5000 | Capital | TRI
P5-14 | Courthouse Parking Lot Lights | Add lights for security/safety | Estimated Cost Per Fiscal Year FY25: 140000 | 140000 | Capital (R) | VC
P5-15 | LW Dog Park | Construct new dog park | Estimated Cost Per Fiscal Year FY25: 10000; Estimated Cost Per Fiscal Year FY26: 25000; Estimated Cost Per Fiscal Year FY27: 50000 | 85000 | Capital | LW
|  |  | Planning | Design | Construction
P5-16 | TRI Sheriff Substation | SO retrofit at SC Complex - TRI - FY24 Fed. Approp. Award | Estimated Cost Per Fiscal Year FY25: 850000; Estimated Cost Per Fiscal Year FY26: 350000 | 1200000 | 25/75 Capital/ Grant * | TRI
|  |  | Construction | Construction
P5-17 | SMAC Elevator |  | Estimated Cost Per Fiscal Year FY25: 125000; Estimated Cost Per Fiscal Year FY26: 1000000 | 1125000 | Building Rest./Grant | VC
|  |  | Design | Construction
P5-18 | SMAC Seismic Retrofit |  | Estimated Cost Per Fiscal Year FY25: 18500; Estimated Cost Per Fiscal Year FY26: 1800000 | 1818500 | Building Rest./Grant | VC
|  |  | Design | Construction
P5-19 | Justice Ct Flagpole |  | Estimated Cost Per Fiscal Year FY25: 15000 | 15000 | Capital (R) | VC
P5-20 | SC Complex Restrooms | Retrofit current single stall to gender specific restrooms | Estimated Cost Per Fiscal Year FY25: 75000 | 300000 | Capital (R) * | TRI
Design
225000
Construction
P5-21 | Piper's Sign | Replace Piper's Opera House Sign | Estimated Cost Per Fiscal Year FY25: 10000 | 10000 | Capital (R) | VC
P5-22 | EM Office Electrical/HVAC | Upgrades | Estimated Cost Per Fiscal Year FY25: 35000 | 35000 | Capital (R) | VC
P5-24 | GH Depot ADA Ramp | ADA Ramp Gold Hill V&T Depot from train to building | Estimated Cost Per Fiscal Year FY26: 50000 | 50000 | Rail | GH
P5-25 | VC Historic Freight Depot ADA Restrooms | Add ADA compliant restrooms | Estimated Cost Per Fiscal Year FY26: 1750000 | 1750000 | Rail | VC
P5-26 | VC Historic Freight Depot Roof | New roof | Estimated Cost Per Fiscal Year FY27: 300000 | 300000 | Rail | VC
P5-27 | CH Generator Replace |  | Estimated Cost Per Fiscal Year FY27: 250000 | 250000 | Capital | VC
P5-28 | Piper's Front Doors/ Southside Windows | Rehabilitate Front Doors FY25 Grant Request | Estimated Cost Per Fiscal Year FY25: 126000 | 126000 | 80/20 Grant/Capital * | VC
P5-29 | MT Network Hookup | Mark Twain Community Center hookup to network | Estimated Cost Per Fiscal Year FY25: 75000 | 75000 | Capital (R) | MT
P5-30 | Swimming Pool Rehab | Planning/design | Estimated Cost Per Fiscal Year FY26: 1000000; Estimated Cost Per Fiscal Year FY27: 10000000 | 11000000 | Capital/ Infrastructure | VC
|  |  |  | Planning/ Design | Construction
P5-31 | IT Office Expansion | 3 conex boxes - moveable/portable | Estimated Cost Per Fiscal Year FY25: 25000 | 25000 | Capital | VC
P5-32 | Countywide Security | Cameras/keyfobs - continuation from FY24 | Estimated Cost Per Fiscal Year FY25: 110000 | 110000 | Capital | Countywide
P5-33 | VC Jail | Construct new facility | Estimated Cost Per Fiscal Year FY25: 1000000; Estimated Cost Per Fiscal Year FY26: 5000000; Estimated Cost Per Fiscal Year FY27: 5000000 | 11000000 | Capital | VC
|  |  | Design | Construction | Construction
P5-34 | VCH Fire Water Cistern | Annually replace 6, add 2 | Estimated Cost Per Fiscal Year FY25: 200000; Estimated Cost Per Fiscal Year FY26: 200000; Estimated Cost Per Fiscal Year FY27: 200000 | 600000 | Capital | VCH
P6-01 | VC Historic Freight Depot Paving | Pave parking area around depot | Estimated Cost Per Fiscal Year FY27: 300000 | 300000 | Rail | VC
P6-05 | LW Outdoor Reader Board | Event Display Board by SO Substation | Estimated Cost Per Fiscal Year FY26: 50000 | 50000 | Capital | LW
P6-06 | C Street Pedestrian Walkway | Feasibility Study Sidewalk from SO to 4th Ward | Estimated Cost Per Fiscal Year FY26: 150000 | 150000 | Capital | VC
P6-07 | Washington St. Stairs | Planning - Replace wood stairs at Washington Street between C & D Streets | Estimated Cost Per Fiscal Year FY26: 23000; Estimated Cost Per Fiscal Year FY27: 110000 | 133000 | Infrastructure | VC
|  |  |  | Planning/ Design | Construction
P6-08 | Restroom C Street | Add public restrooms by DA Office | Estimated Cost Per Fiscal Year FY26: 50000; Estimated Cost Per Fiscal Year FY27: 450000 | 500000 | VCTC | VC
|  |  |  | Planning/ Design | Construction
P6-09 | Piper's Structural Retrofit | ADA access and interior improvements | Estimated Cost Per Fiscal Year FY27: 600000 | 600000 | Piper's | VC
P6-11 | LW PW Fuel Tank | Replace double-lined fuel tank at LW Fire Station 74 | Estimated Cost Per Fiscal Year FY26: 315000 | 315000 | Capital | LW
P6-13 | Mobile EOC | FY25 Federal Appropriation Request | Estimated Cost Per Fiscal Year FY26: 250000 | 250000 | Grant/Capital | Countywide
P6-14 | TRI PW Shop | PW equipment barn at Storey County Complex | Estimated Cost Per Fiscal Year FY29: 3400000 | 3400000 | Capital | TRI
P6-15 | Piper's A Street | PER/ER/Design Phase - FY25 Fed Approp - West Wall Infiltration/ Stability | Estimated Cost Per Fiscal Year FY26: 1100000; Estimated Cost Per Fiscal Year FY27: 842850 | 1942850 | Grant/Capital | VC
|  |  |  | PER/ Design | Construction
P6-16 | B Street Barn | Structural assessment | Estimated Cost Per Fiscal Year FY26: 10000 | 10000 | Capital | VC
P6-18 | VC Sr. Center Fence Replace | Replace chainlink fence with historically appropriate material | Estimated Cost Per Fiscal Year FY26: 10000 | 10000 | Capital | VC
P6-19 | Service Department Extension | Expand/Construct Vehicle Service Department - Feasibility Study | Estimated Cost Per Fiscal Year FY26: 100000 | 100000 | Capital | TRI/VC
P7-01 | Security Key Fobs | Entrance security system PW | Estimated Cost Per Fiscal Year FY25: 75000 | 75000 | Capital | TRI/VC
P7-02 | Courthouse Earthquake Retrofit |  | Estimated Cost Per Fiscal Year FY27: 1800000 | 1800000 | Capital | VC
P7-03 | Baseball Field Upgrades | Lights, backboard, pavers | Estimated Cost Per Fiscal Year FY27: 100000 | 100000 | Parks | VC
P7-04 | GH Depot Parking | Implement results from FY26 study - Paving | Estimated Cost Per Fiscal Year FY27: 250000 | 250000 | Rail | GH
P7-05 | Piper's Electrical | Upgrade service to 600A | Estimated Cost Per Fiscal Year FY27: 750000 | 750000 | Piper's | VC
P7-06 | Piper's Kitchen | Upgrade kitchen | Estimated Cost Per Fiscal Year FY27: 60000 | 60000 | Piper's | VC
P7-07 | Dispatch Center | New facility | Estimated Cost Per Fiscal Year FY29: 10000000 | 10000000 | Capital | VC
P7-08 | VCH Mailbox Plaza | New mailbox plaza - Commissioner Request | Estimated Cost Per Fiscal Year FY27: 150000; Estimated Cost Per Fiscal Year FY28: 1350000 | 1500000 | Capital | VCH
[5 empty] | Design | Construction
P7-09 | Outdoor Shooting Range |  | Estimated Cost Per Fiscal Year FY27: 400000 | 400000 | Capital | Countywide
P7-10 | SMAC Generator | Purchase/install | Estimated Cost Per Fiscal Year FY27: 100000 | 100000 | Building Rest./Grant | VC
P8-01 | LCC Gas Lines | Replace gas distribution lines throughout LCC | Estimated Cost Per Fiscal Year FY28: 500000 | 500000 | Infrastructure | LW
P8-02 | MT Drainage | Implement DVADMP Master Plan | Estimated Cost Per Fiscal Year FY28: 12000000 | 12000000 | Capital/Infra | MT
P8-03 | MT Landscaping | Add landscaping, trees, irrigation around MTCC | Estimated Cost Per Fiscal Year FY28: 100000 | 100000 | Capital | MT
P8-04 | MT Parking Lot | Repave Parking Lot | Estimated Cost Per Fiscal Year FY28: 200000 | 200000 | Capital | MT
P8-06 | VC Sr. Center Generator | Purchase/install, electrical upgrades | Estimated Cost Per Fiscal Year FY28: 400000 | 400000 | Capital | VC
P8-07 | EOC | Emergency Operation Center located near SR 341 | Estimated Cost Per Fiscal Year FY28: 1500000 | 1500000 | Capital | VCH
P8-08 | LW Land Acquisition | Acquire vacant land north of Rainbow Bend from Washoe Co. | Estimated Cost Per Fiscal Year FY28: 1000000 | 1000000 | Capital | LW
P8-09 | Piper's HVAC/Plumbing | Add 60 gallon h20 heater, heating, cooling, ventilation | Estimated Cost Per Fiscal Year FY28: 400000 | 400000 | Piper's | VC
P8-10 | Piper's Carriage House | Prep opening for Carriage house doors, rebuild doors | Estimated Cost Per Fiscal Year FY30: 70000 | 70000 | Piper's | VC
P8-11 | Piper's Balcony | Balcony Repairs | Estimated Cost Per Fiscal Year FY30: 1000000 | 1000000 | Piper's | VC
P8-12 | Piper's Generator |  | Estimated Cost Per Fiscal Year FY28: 100000 | 100000 | Piper's | VC
P8-14 | Historic Taylor Street Stairs | Recreate stairs from C to B Street | Estimated Cost Per Fiscal Year FY28: 35000; Estimated Cost Per Fiscal Year FY29: 150000 | 185000 | Capital | VC
[6 empty] | Design | Construction
P9-01 | Piper's Seismic Retrofit |  | Estimated Cost Per Fiscal Year FY29: 1800000 | 1800000 | Capital | VC
P9-04 | TRI Justice Center | Add justice complex to Storey County Government Complex | Estimated Cost Per Fiscal Year FY29: 4000000 | 4000000 | Capital | TRI
P9-05 | Parking Garage | Construct Parking Garage | Estimated Cost Per Fiscal Year FY29: 1000000; Estimated Cost Per Fiscal Year FY30: 20000000 | 21000000 | Capital/Infra | VC
[7 empty] | Design | Construction
P9-06 | Fairgrounds Restrooms | Construct ADA Restrooms | Estimated Cost Per Fiscal Year FY29: 75000; Estimated Cost Per Fiscal Year FY30: 500000 | 575000 | Capital | VC
[7 empty] | Design | Construction
P0-01 | Fourth Ward Generator | Purchase/install | Estimated Cost Per Fiscal Year FY30: 100000 | 100000 | Capital | VC
P0-02 | Gold Hill Depot Generator | Purchase/install | Estimated Cost Per Fiscal Year FY30: 15000 | 15000 | Capital | GH
P0-03 | VC Depot Generator | Purchase/install | Estimated Cost Per Fiscal Year FY30: 15000 | 15000 | Capital | VC
P0-04 | Comptroller Generator | Purchase/install | Estimated Cost Per Fiscal Year FY30: 100000 | 100000 | Capital | VC
Project Totals Per FY |  |  | 14193500 | 22576000 | 22237850 | 17585000 | 20425000 | 21800000 | 118817350
ROADS
R4-43 | Lousetown Road Rehab | Began FY24 | Estimated Cost Per Fiscal Year FY25: 2634460 | 2634460 | Roads | VCH
R4-45 | Six Mile Turnaround | Began FY24 - Cooperation Lyon Co. | Estimated Cost Per Fiscal Year FY25: 320000 | 320000 | Roads | 6 Mile
R5-40 | Countywide Road Projects | Per DOWL CIP | Estimated Cost Per Fiscal Year FY25: 3308582; Estimated Cost Per Fiscal Year FY26: 3400000; Estimated Cost Per Fiscal Year FY27: 7100000 | 13808582 | Infra/Roads | Countywide
R5-42 | Fairgrounds Rd. RR | Realign/properly signal RR crossing at Fairgrounds Road/F Street | Estimated Cost Per Fiscal Year FY27: 1000000 | 1000000 | Roads/Rail | VC/6 Mile
R5-43 | LW Flood Mitigation Implementation | Implement LW Flood Mitigation Study Alt. #3 Rank #2 - Dependent upon award of CPF request (federal funding) in the beginning of calendar year 2025 | Estimated Cost Per Fiscal Year FY25: 25000; Estimated Cost Per Fiscal Year FY26: 4636553 | 4661553 | Grant/Roads * | LW
R5-44 | Traffic Signal Milan/Electric | 85% Tesla to reimburse - $1,572,500 - with a cap | Estimated Cost Per Fiscal Year FY25: 150000 | 2000000 | Capital (R) * | TRI
Design
1850000
Construction
R5-45 | Six Mile Culverts | Implement Six Mile drainage study - culverts - $36,000 grant award | Estimated Cost Per Fiscal Year FY26: 170000 | 170000 | Grant/ Planning | VC/6 Mile
R6-41 | Six Mile Flood Mitigation | Implement Six Mile drainage study - Projects 1, 2, 3 | Estimated Cost Per Fiscal Year FY26: 7300000 | 7300000 | Capital/Roads | VC/6 Mile
R6-43 | SR 341 Retaining Wall | Reconstruct retaining wall - residence of N SR341 | Estimated Cost Per Fiscal Year FY26: 50000 | 50000 | Roads | VC/6 Mile
R8-41 | Northwest Pedestrian Improvements | West side of C St. from Sutton to Carson St - Feasibility Study | Estimated Cost Per Fiscal Year FY28: 240000 | 240000 | Roads | VC
R8-42 | Northeast Pedestrian Improvements | East side of C St. from Sutton to Carson St - Feasibility Study | Estimated Cost Per Fiscal Year FY28: 240000 | 240000 | Roads | VC
R8-43 | North Bridge Pedestrian Improvements | East side of C St. bridge/overhang over lower parking lot segment - Feasibility Study | Estimated Cost Per Fiscal Year FY28: 360000 | 360000 | Roads | VC
R9-40 | Cemetery East Access | Culvert and dirt road over drainage at SE corner of cemetery for access per MOU | Estimated Cost Per Fiscal Year FY29: 100000 | 100000 | Roads | VC
R9-41 | Realign Toll Rd at CCI | Realign West end so it matches county property - Work with Community Chest (Pending Hillside/Divide Looping W6-52) | Estimated Cost Per Fiscal Year FY29: 450000 | 450000 | Roads | VC
R9-42 | Sydney Cul-de-sac | Correct cul-de-sac at Sydney Drive to remove GID Building and drainages | Estimated Cost Per Fiscal Year FY29: 1000000 | 1000000 | Roads | TRI
Roads Totals Per FY |  |  | 8288042 | 15556553 | 8100000 | 840000 | 1550000 | 0 | 34334595
STUDIES and PLANS
S5-90 | TRI Drainage Study | Drainage needs for TRI on County-owned roads and parcels | Estimated Cost Per Fiscal Year FY25: 250000 | 250000 | Planning | TRI
S5-91 | Fairgrounds Traffic Study | Evaluate traffic control needs for upgraded Fairgrounds - Commissioner Request | Estimated Cost Per Fiscal Year FY25: 150000 | 150000 | Capital | VC
S5-92 | Countywide Facilities Study | Evaluate facility feasibility needs of entire County | Estimated Cost Per Fiscal Year FY25: 150000 | 150000 | 101 | Countywide
S6-90 | GH Depot Land Survey | Survey & reconsolidate land around Gold Hill Depot | Estimated Cost Per Fiscal Year FY26: 20000 | 20000 | Rail | GH
S6-91 | GH Drainage Study | Evaluate drainage needs for Gold Canyon, Gold Hill, American Flat - Fully funded by CWSD (Pending) | Estimated Cost Per Fiscal Year FY25: 5000 | 5000 | Planning/100% Reimburse CWSD | GH
S6-92 | VCH Water Plan | Update 2022 Water Master Plan for VCH water distribution system | Estimated Cost Per Fiscal Year FY26: 20000 | 20000 | Water | VCH
S6-93 | Road Abandon Study | Determine what roads may be considered for future abandonment | Estimated Cost Per Fiscal Year FY27: 100000 | 100000 | Planning | Countywide
S6-94 | VC Parking Study | Update to 1992 Virginia City Parking Study | Estimated Cost Per Fiscal Year FY25: 75000; Estimated Cost Per Fiscal Year FY26: 75000 | 150000 | Planning | VC
S7-90 | Roads CIP VC | Update Roads CIP | Estimated Cost Per Fiscal Year FY27: 100000 | 100000 | Roads | Countywide
S8-90 | Master Plan Update | 10-year Storey County Master Plan update consultation/technical assistance | Estimated Cost Per Fiscal Year FY25: 100000 | 100000 | Planning | Countywide
Studies and Plans Totals Per FY |  |  | 730000 | 115000 | 200000 | 0 | 0 | 0 | 1045000
WATER
W5-51 | Water Treat Recirc. | Replace open bodies with tank - split between 2 FYs - Began in FY24 | Estimated Cost Per Fiscal Year FY25: 55261 | 55261 | Infra | VC
Design
W5-52 | Water Tank Upgrades | Repair/seal water tanks | Estimated Cost Per Fiscal Year FY25: 85000; Estimated Cost Per Fiscal Year FY26: 85000; Estimated Cost Per Fiscal Year FY27: 85000 | 255000 | Infra | VC
W5-53 | Silver City Water Main | Water main replacement between Gold Hill/Silver City - Began FY24 | Estimated Cost Per Fiscal Year FY25: 65996; Estimated Cost Per Fiscal Year FY26: 2376000 | 2441996 | Water * | GH/SC
|  |  | Design/ Permitting | Construction
W5-56 | Gold Hill Collection System | Rehabilitation - FY24 Fed Approp Award | Estimated Cost Per Fiscal Year FY25: 500000; Estimated Cost Per Fiscal Year FY26: 3250000 | 3750000 | 25/75 Capital/ Grant * | GH
|  |  | Design | Construction
W5-57 | Lead Siphon Replacement |  | Estimated Cost Per Fiscal Year FY25: 1150000 | 1150000 | Grant * | VC
Design/ Principal forgiveness loan
W6-50 | Water Plant Valves | Replace Limitorque Control Packs | Estimated Cost Per Fiscal Year FY26: 200000 | 200000 | Infrastructure | VC
W6-52 | Hillside to Divine Main | Water transmission main replacement - FY25 Fed. Approp. Request | Estimated Cost Per Fiscal Year FY26: 75000; Estimated Cost Per Fiscal Year FY27: 925000 | 1000000 | Grant/Water * | VC
|  |  |  | PER/ Design | Construction
W8-50 | 5 Mile Reservoir Wall | Wall surrounding 5 Mile Reservoir | Estimated Cost Per Fiscal Year FY30: 720000 | 720000 | Water | VC
W8-51 | Water Treatment Plant Wall | Wall abutting south of water treatment ponds | Estimated Cost Per Fiscal Year FY28: 360000 | 360000 | Water | VC
W8-52 | Gold Hill Sewer Expansion | Expand current facility x2 to facilitate new residential/commercial construction (Pending W5-51) | Estimated Cost Per Fiscal Year FY28: 5000000 | 5000000 | Water | GH
Water Totals Per FY |  |  | 1856257 | 5986000 | 1010000 | 5360000 | 0 | 720000 | 14932257
Totals by FY |  |  | 26614799 | 46548553 | 35237850 | 24825000 | 22860000 | 22520000 | 178606202
2031 and BEYOND PROJECTS
P6-17 | IT Data Center Relocation | Cost estimate $4 million in FY24 - Factoring in FY24 rate of inflation over 6 years. | Estimated Cost Per Fiscal Year FY25: 10000000 |  | Capital | VC
P9-02 | Piper's Repairs | Complete stairs to balcony, restroom exhaust fans, replace missing finials | Estimated Cost Per Fiscal Year FY25: 50000 |  | Piper's | VC
P9-03 | Piper's Exterior | Repaint/repair brick & mortar, replace exterior egress stairs north side | Estimated Cost Per Fiscal Year FY25: 170000 |  | Piper's | VC
| South VC Rest Stop | Restrooms, Parking, Visitor Information Kiosks | Estimated Cost Per Fiscal Year FY25: 2000000 |  | VCTC | VC
| Inclinator F to C Street | From VC Freight Depot (multi-modal transit hub) to C St. | Estimated Cost Per Fiscal Year FY25: 1000000 |  | VCTC | VC
| VCTC Visitor's Center | Rehab or move to new location | Estimated Cost Per Fiscal Year FY25: 500000 |  | VCTC | VC
|  |  | Estimated Cost Per Fiscal Year FY28: Project ID Key |  | Funding Source Key
|  |  | Estimated Cost Per Fiscal Year FY28: Example: E4-66 |  | R - Roll from previous year
|  |  | Estimated Cost Per Fiscal Year FY28: Letters; Estimated Cost Per Fiscal Year FY29: 1st Number; Estimated Cost Per Fiscal Year FY30: 2nd Numbers |  | * - Object code in Tyler
[6 empty] | E - Equipment | Last digit of fiscal year. In example the 4 is FY24 | 60 through 89
[6 empty] | P - Projects |  | 1 through 39
[6 empty] | R - Roads |  | 40 through 49
[6 empty] | S - Studies |  | 90 through 99
[6 empty] | W - Water |  | 50 through 59

## Additional Project Details
Project ID | Project Name | Project Contact | FTE
EQUIPMENT
E4-66 | GMC Buildings/Grounds | PW | N/A
E5-60 | Road Sweeper | PW | N/A
E5-61 | Short-Frame Plow | PW | N/A
E5-62 | Peterbuilt Dump Truck/Plow/Sander | PW | N/A
E5-63 | Skippy Tractor | PW | N/A
E5-64 | Light Plant w. Solar | PW | N/A
E5-65 | GMC Water/Sewer | PW | N/A
E5-69 | Compactors | PW | N/A
E5-70 | Patrol Vehicle Rotation | SO | N/A
E5-71 | Patrol Vehicle Rotation | SO | N/A
E5-72 | Patrol Vehicle Rotation | SO | N/A
E5-73 | Patrol Vehicle Rotation | SO | N/A
E5-74 | Tesla | SO | N/A
E5-75 | RAM 5500 crew-cab utility | PW | N/A
E5-76 | RAM 5500 crew-cab utility | PW | N/A
E5-79 | Skid Steer Snowblower | PW | N/A
E5-80 | 125' Boom Lift | PW | N/A
E5-81 | Pickup | PW | N/A
E5-82 | Pickup | PW | N/A
E5-83 | Electronic Reader Board | PW | N/A
E6-60 | PW Peterbuilt Dump Truck | PW | N/A
E6-61 | PW Service Truck | PW | N/A
E6-62 | PW John Deere Loader | PW | N/A
E6-63 | PW Dump Truck | PW | N/A
E6-64 | PW Motor Grader | PW | N/A
E6-65 | PW Screened Grizzly | PW | N/A
E6-66 | Patrol Vehicle Rotation | SO | N/A
E6-67 | Patrol Vehicle Rotation | SO | N/A
E6-68 | Patrol Vehicle Rotation | SO | N/A
E6-69 | Com. Dev. Pick-up | PW | N/A
E6-70 | EM UTV | PW | N/A
E6-71 | Electronic Reader Board | PW | N/A
E7-60 | Service Truck | PW | N/A
E7-61 | Water Truck | PW | N/A
E7-62 | Motor Grader | PW | N/A
E7-63 | Ditch Compactor | PW | N/A
E7-64 | Small Backhoe/loader | PW | N/A
E7-65 | Road Manager Truck | PW | N/A
E7-66 | 5-Yard AWD Dump Truck | PW | N/A
E7-67 | Tractor Trailer | PW | N/A
E7-68 | Vactor Truck | PW | N/A
E7-69 | Patrol Vehicle Rotation | SO | N/A
E7-70 | Patrol Vehicle Rotation | SO | N/A
E7-71 | Patrol Vehicle Rotation | SO | N/A
E7-72 | Service Equipment | PW | N/A
E7-73 | Backhoe | PW | N/A
E7-74 | Loader | PW | N/A
E8-60 | GMC 3500 Truck | PW | N/A
E8-61 | Pickup | PW | N/A
E8-62 | Pickup | PW | N/A
E8-63 | Service Truck | PW | N/A
E8-64 | Staff Vehicle | PW | N/A
E8-65 | Staff Vehicle | PW | N/A
E8-66 | Staff Vehicle | PW | N/A
E8-67 | Staff Vehicle | PW | N/A
E8-68 | Staff Vehicle | PW | N/A
E8-69 | Staff Vehicle | PW | N/A
E8-70 | Patrol Vehicle | SO | N/A
E8-71 | Patrol Vehicle | SO | N/A
E8-72 | Patrol Vehicle | SO | N/A
E9-60 | Multi-Use Truck | PW | N/A
E9-61 | Excavator | PW | N/A
E9-62 | Street Sweeper | PW | N/A
E9-63 | Forklift | PW | N/A
E9-64 | Snow Cat | PW | N/A
PROJECTS
P3-01 | Courthouse Fence Repair | MN, AO
P4-07 | Fairgrounds Upgrade | MN
P4-08 | LW Fiber | JD
P4-11 | Lockwood Sr. Center | MN
P4-12 | Fire Station 71 | MN
P4-13 | Fuel Tanks | TS, MN
P4-15 | MTCC Outdoor Reader Board | KC
P4-18 | Com. Dev. Generator | MN
P4-19 | Waste Water Tower Fencing | JD
P4-20 | TRI Monument Signs | LM
P5-01 | Justice Ct/IT Generator | MN
P5-02 | Gold Hill Sewer Generator | MN
P5-03 | VC Parcourse | MN, KC
P5-04 | LAN | JD
P5-06 | PW Portable Fencing | JH
P5-07 | MT Community Center | MN
P5-08 | Com. Dev. Parking | MN, JW
P5-09 | Com. Dev. Mudroom | MN, JW
P5-11 | VCH Swing Set | JW
P5-12 | VCH Community Center | MN
P5-13R | SC Gov. Complex Sign | LM
P5-14 | Courthouse Parking Lot Lights | JW, JH
P5-15 | LW Dog Park | KC
P5-16 | TRI Sheriff Substation | MN
P5-17 | SMAC Elevator | AP, SS
P5-18 | SMAC Seismic Retrofit | AP, SS
P5-19 | Justice Ct Flagpole | MN
P5-20 | SC Complex Restrooms | MN
P5-21 | Piper's Sign | JH
P5-22 | EM Office Electrical/HVAC | JH, MN, JW
P5-24 | GH Depot ADA Ramp | MN
P5-25 | VC Historic Freight Depot ADA Restrooms | MN
P5-26 | VC Historic Freight Depot Roof | MN
P5-27 | CH Generator Replace | TS
P5-28 | Piper's Front Doors/ Southside Windows | SS, LM, JH
P5-29 | MT Network Hookup | JD
P5-30 | Swimming Pool Rehab | JW, JH
P5-31 | IT Office Expansion | MN, JD
P5-32 | Countywide Security | JD
P5-33 | VC Jail | MN, LM, SS
P5-34 | VCH Fire Water Cistern | Fire
P6-01 | VC Historic Feight Depot Paving | MN
P6-05 | LW Outdoor Reader Board | KC
P6-06 | C Street Boardwalk
P6-07 | Washington St. Stairs
P6-08 | Restroom C Street
P6-09 | Piper's Structural Retrofit | SS, LM
P6-11 | LW PW Fuel Tank | TS
P6-13 | Mobile EOC | AW, SS, LM
P6-14 | TRI PW Shop | Pub Works
P6-15 | Piper's A Street | SS, LM
P6-16 | B Street Barn | MN
P6-18 | VC Sr. Center Fence Replace | MN
P7-01 | Security Key Fobs | JD
P7-02 | Courthouse Earthquake Retrofit
P7-03 | Baseball Field Upgrades | JF
P7-04 | GH Depot Parking | JW
P7-05 | Piper's Electrical
P7-06 | Piper's Kitchen
P7-07 | Dispatch Center
P7-08 | VCH Mailbox Plaza
P7-09 | Outdoor Shooting Range | MN, SS
P7-10 | SMAC Generator | AP
P8-01 | LCC Gas Lines | AO
P8-02 | MT Drainage | KC
P8-03 | MT Landscaping
P8-04 | MT Parking Lot
P8-06 | VC Sr. Center Generator
P8-07 | EOC | AW
P8-08 | LW Land Acquisition | AO
P8-09 | Piper's HVAC/Plumbing
P8-10 | Piper's Carriage House
P8-11 | Piper's Balcony
P8-12 | Piper's Generator
P8-14 | Historic Taylor Street Stairs
P9-01 | Piper's Seismic Retrofit
P9-04 | TRI Justice Center
P9-05 | Parking Garage
P9-06 | Fairgrounds Restrooms
P0-01 | Fourth Ward Generator
P0-02 | Gold Hill Depot Generator
P0-03 | VC Depot Generator
P0-04 | Comptroller Generator
ROADS
R4-43 | Lousetown Road Rehab | JW, AO
R4-45 | Six Mile Turnaround | MN
R5-40 | Countywide Road Projects | JW
R5-42 | Fairgrounds Rd. RR
R5-43 | LW Flood Mitigation Implementation | LM, SS, KC
R5-44 | Traffic Signal Milan/Electric | MN
R5-45 | Six Mile Culverts | KC, MN
R6-41 | Six Mile Flood Mitigation
R6-43 | SR 341 Retaining Wall
R8-41 | Boardwalk Northwest
R8-42 | Boardwalk Northeast
R8-43 | Boardwalk North Bridge
R9-40 | Cemetery East Access | AO
R9-41 | Realign Toll Rd at CCI
R9-42 | Sydney Cul-de-sac
STUDIES and PLANS
S5-90 | TRI Drainage Study | KC
S5-91 | Fairgrounds Traffic Study | MN
S5-92 | Countywide Facilities Study | AO
S6-90 | GH Depot Land Survey | KC, SS
S6-91 | GH Drainage Study | KC
S6-92 | VCH Water Plan | AO
S6-93 | Road Abandon Study | KC
S6-94 | VC Parking Study | KC
S7-90 | Roads CIP VC | JW
S8-90 | Master Plan Update | KC
WATER
W5-51 | Water Treat Recirc. | JW
W5-52 | Water Tank Upgrades | MN, JW
W5-53 | Silver City Water Main | JW
W5-56 | Gold Hill Collection System | JW, SS
W5-57 | Lead Siphon Replacement | JW, SS
W6-50 | Water Plant Valves | JW
W6-52 | Hillside to Divide Main | JW, SS
W8-50 | 5 Mile Reservoir Wall
W8-51 | Water Treatment Plant Wall
W8-52 | Gold Hill Sewer Expansion
2031 and BEYOND PROJECTS
P6-17 | IT Data Center Relocation
P9-02 | Piper's Repairs
P9-03 | Piper's Exterior
South VC Rest Stop
Inclinator F to C Street
VCTC Visitor's Center